## Task List
Club Renovation and Reopening Task List
|  | Grand Reopening Event Date | Today's Date | Due Date Legend
|  | 2022-12-14 | 2023-04-24 | This Week
|  | Renovation Start Date |  | Next Week
|  | 2022-11-07 |  | Last Week
Renovation Complete Date
2022-12-05
[5 empty] | Preparing for Renovation | [5 empty] | During Renovation & Construction |  |  |  | Renovation Complete
|  | Phase and Tasks | Date Due | Complete | GO-10 Wks | GO-9 Wks | GO-8 Wks | GO-7 Wks | GO-6 Wks | GO-5 Wks | GO-4 Wks | GO-3 Wks | GO-2 Wks | GO-1 Wk | GO! | GO+1 Wk | GO+2 Wks | GO+3 Wks | GO+4 Wks
Preparing for Renovation
1 | FALSE | Develop renovation & reopening marketing plan & budget | 2022-09-26
2 | FALSE | Determine renewal, referral and acquisition offers | 2022-09-26
3 | FALSE | Plan paid digital and print advertising activities | 2022-09-28
4 | FALSE | Plan owned media (social, web) to keep people updated | 2022-09-28
5 | FALSE | Create marketing assets and order promotional signage | 2022-10-03
6 | FALSE | Order branded gifts and/or promotional items and staff uniforms | 2022-10-03
7 | FALSE | Hold all-staff meeting | 2022-10-10
8 | FALSE | Offer and promote renewal and referral incentives | 2022-10-17
9 | FALSE | Hang mood board with elements of remodel, announce renovation | 2022-10-20
10 | FALSE | Email to member base #1 (announce renovation, renewal offers) | 2022-10-20
11 | FALSE | Post to social media #1 (announce renovation, renewal offers) | 2022-10-20
12 | FALSE | Plan your grand reopening event | 2022-10-24
13 | FALSE | Connect with marketing(s) vendor to schedule paid media | 2022-10-24
14 | FALSE | Email member base #2 (Start date, affected amenities if staying open) | 2022-10-31
15 | FALSE | Organic social post #2 (Start date, affected amenities if staying open) | 2022-10-31
16 | FALSE | Post closure or disruption details sign on club door | 2022-10-31
17 | FALSE | Email member base #3 (Closure Details/Affected Amenities) | 2022-11-06
18 | FALSE | Organic social post #3 (Closure Details/Affected Amenities) | 2022-11-06
19 |  | Update Google My Business in Soci to reflect temporary closure | 2022-11-06
During Renovation & Construction
20 | FALSE | Construction - Organic Social Posts #1/Email #1 - Updates, progress photos and announcements | 2022-11-14
21 | FALSE | Construction - Organic Social Posts #2/Email #2 - Updates, progress photos and announcements | 2022-11-21
22 | FALSE | Construction - Organic Social Posts #3/ Email #3 - Updates, progress photos and announcements | 2022-11-28
23 | FALSE | Construction - Organic Social Posts #4/Email #4 - Updates, progress photos and announcements | 2022-12-05
24 | FALSE | Schedule and promote offsite or outdoor workouts | 2022-11-21
25 | FALSE | Start community outreach per marketing plan | 2022-11-21
26 | FALSE | Prepare gifts and give aways for event | 2022-11-30
27 | FALSE | Promote grand reopening event, including paid media | 2022-11-30
Renovation Complete
28 | FALSE | Email message of appreciation to staff and members, renovation complete | 2022-12-06
29 |  | Update all owned media (web, social, GMB) with new photos, logos | 2022-12-06
30 | FALSE | Post reopening/renovation complete announcement to social media | 2022-12-07
31 | FALSE | Run paid media campaign with new member offer | 2022-12-07
32 | FALSE | Install temp signage/banners/balloons etc. to promote grand reopening | 2022-12-07
33 | FALSE | Host grand reopening event | 2022-12-14
34 | FALSE | Evaluate marketing plan performance (paid media and guerilla tactics) | 2023-01-11
Custom Tasks
35 | FALSE
36 | FALSE
37 | FALSE
38 | FALSE
39
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 1
Check Box 30
Check Box 30
Check Box 30
Check Box 30
Check Box 30
Check Box 30
Check Box 1
Check Box 30